## Taho IT Remediation
IT Self Assessment
Average
|  |  |  | Defined | 2.71 |  |  | Folder: 202209-Taiwan BU self-assessment
Internal Control Code | Domain | Sub-Domain | Self Assessment questionnaire | Maturity Level | Score | Comments |  | Document Link | Remediation Requirements | Year | Asia SCEC | Group Task Force | Maturity Lv. : Defined | Chinese Maturity Lv. : Defined | Remediation Plan | Chinese Remediation Plan | Action Plan | CAPEX (K Local Currency) | OPEX (K Local Currency ) | Responsible | Due Date | Status | Remediation Track | To do # | Completed #
CY-IT101 | Identify | Governance | Do you currently have a Chief Information Security Officer (CISO) and an associated organization defined within your entity? | Defined | 3 | 文件已制定，送審及等待發布中 | The document has been drafted and is awaiting review and release. | https://docs.google.com/document/d/1zUe3JQWBnb8q_kxQhNPl7utj-YS825K_/edit?usp=share_link&ouid=112652071405849358717&rtpof=true&sd=true | - People - The Chief Information Security Officer (CISO) or the Cyber Security Correspondent. Role(s) is defined to manage and be responsible to the cyber security functions. - Process - Documented scope and the cyber security function at BU/Project Level. - Deliverables - The job description of the CISO or the Cyber Security Correspondent. - Deliverables - The organization chart with the cyber security Role(s)/team at BU/Project Level and shared with Group/Zone CISOs. | 2023 | * Create the management document template | * the simlar template as the one of OT | - People - The Chief Information Security Officer (CISO) or the Cyber Security Correspondent. Role(s) is defined to manage and be responsible to the cyber security functions. - Process - Documented scope and the cyber security function at BU/Project Level. - Deliverables - The job description of the CISO or the Cyber Security Correspondent. - Deliverables - The organization chart with the cyber security Role(s)/team at BU/Project Level and shared with Group/Zone CISOs. | - 人 - 首席信息安全官（CISO）或网络安全通讯员。角色被定义为管理和负责网络安全功能。 - 流程 - 在BU/项目级别记录的范围和网络安全功能。 - 可交付成果 - CISO或网络安全通讯员的职位描述。 - 可交付成果 - 具有网络安全角色/团队在BU/项目级别的组织图表，并与Group/Zone Cisos共享。 | * Create information security management documents, cover the required content. * Description of the personnel of the person in charge of the office network information security * Organizational architecture of office network information security | * 创建信息安全管理文件，涵盖所要求的内容。 * 办公网络信息安全负责人的岗位职责描述 * 办公网络信息安全的组织架构图 | [7 empty] | 1 | 0
CY-IT102 | Identify | Dedicated cybersecurity budget | Do you have an annual budget dedicated to cybersecurity within your entity? | Defined | 3 | Have the cyber security budget every year | Have the cyber security budget every year | https://docs.google.com/spreadsheets/d/1fYyLbyJqcS9clGC6WKBIT4RoPqD7-b-wECRQQnEQrbo/edit#gid=609546198 | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - Cyber Security Budget Plan defined and submitted for approval (Following Group Standard Templated) - Deliverables - Security Action Plan covered in the budget plan which are endorsed by Group / Zone / BU CISO | 2023 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - Cyber Security Budget Plan defined and submitted for approval (Following Group Standard Templated) - Deliverables - Security Action Plan covered in the budget plan which are endorsed by Group / Zone / BU CISO | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 网络安全预算计划定义并提交批准（以下是小组标准模板） - 可交付成果 - 预算计划中涵盖的安全行动计划，该计划由小组 /区域 / BU CISO认可 | * Create information security management documents, cover the required content. * Use the group's information security budget template to formulate budgets, and hand in management for approval | * 创建信息安全管理文件，涵盖所要求的内容。 * 使用集团信息安全预算模板制定预算，并交管理层审批 | Need 1) budget amount calculation description; 2) expese approval record against the busget 1. Cyber Security Budget Plan defined and submitted for approval (Following Group Standard Templated) 2. Security Action Plan covered in Budget plan that are endorsed by Group / Zone / BU CISO 3. Regular spending Review. (at least every 6 months) udpated to Zone/BU Level | [6 empty] | 1 | 0
CY-IT103 | Identify | Assets Inventory | Do you maintain a regularly updated list of all physical assets (servers, workstations, smartphones, firewalls, switches, VPN concentrators, etc.) and application assets (software, applications, etc.) with an evaluation of the criticality of each of these assets in your entity? | Defined | 3 | 有，並有資訊系統進行管控 | Yes, and there is an information system for control. | https://glpi.tahoho.com.tw/ https://drive.google.com/file/d/1yJ40yC2tmKizmi1IU52FEOHMfcLB6mkG/view?usp=share_link | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The updated list of physical assets. - Deliverables - The updated list of application assets. - Deliverables (IT only) - The asset catalog with the criticality defined. | 2023 | * Create the management document template | * IT inventory template | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The updated list of physical assets. - Deliverables - The updated list of application assets. - Deliverables (IT only) - The asset catalog with the criticality defined. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 实际资产的更新列表。 - 可交付成果 - 更新的应用程序资产列表。 - 可交付成果（仅此） - 具有关键性定义的资产目录。 | * Create information security management documents, cover the required content. * According to the group's asset list template, update the asset list in time, in the asset list, you should mark whether it is an important asset, whether there is an Internet link, etc. | * 创建信息安全管理文件，涵盖所要求的内容。 * 按照集团资产清单模板及时更新资产清单记录，在资产清单中应该标注是否是重要资产、是否有互联网链接等 | [7 empty] | 1 | 0
CY-IT104 | Identify | Risk Management | Do you have a recent risk analysis (last update within the last year) and an associated action plan? | Defined | 3 | 有 | have | https://docs.google.com/spreadsheets/d/1IQp2xAmWwMfKO05Z9OQhyZmZkoeCeoWe/edit?usp=share_link&ouid=112652071405849358717&rtpof=true&sd=true | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The cyber security risk analysis report with the remediation action plan at least once a year - Deliverables - The records of remediation actions for the findings | 2023 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The cyber security risk analysis report with the remediation action plan at least once a year - Deliverables - The records of remediation actions for the findings | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 每年至少每年至少每年一次的网络安全风险分析报告 - 可交付成果 - 调查结果的补救措施记录 | * Create information security management documents, cover the required content. * Do self -assessment once a year and rectify * Do the risk assessment once a year (the most risk items, 2 to 5), and rectify the rectification (The above two evaluations and rectification can be arranged together) | * 创建信息安全管理文件，涵盖所要求的内容。 * 每年做一次自评估，并整改 * 每年做一次风险评估（风险最高的项目，2至5个），并整改 （上述两项评估和整改可以安排一起做） | [7 empty] | 1 | 0
CY-IT105 | Identify | Dashboard | Are you using the Compliance Dashboard or a Dashboard with relevant cybersecurity KPIs to monitor and communicate your level of cybersecurity? | Defined | 3 | 有，Security KPI | Yes, Security KPI | https://drive.google.com/file/d/1ozrf7LJyAqvqiy9LiB_ouCYvRjj0-bDH/view?usp=share_link | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - A cyber security Compliance/KPI dashboard reports and communicated with the management. - Deliverables - Records of Remediation actions of risks and non-compliance. | 2023 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - A cyber security Compliance/KPI dashboard reports and communicated with the management. - Deliverables - Records of Remediation actions of risks and non-compliance. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 网络安全合规性/KPI仪表板报告并与管理层进行了通信。 - 可交付成果 - 风险和违规行为的补救措施记录。 | * Create information security management documents, cover the required content. * Multi -monthly network security compliance/KPI instrument board report and communicate with management. * Remedial measures for identification risks and violations and records. | * 创建信息安全管理文件，涵盖所要求的内容。 * 每月发网络安全合规性/KPI仪表板报告并与管理层进行了通信。 * 对于识别的风险和违规行为采取补救措施，并记录。 | [7 empty] | 1 | 0
CY-IT106 | Identify | Third Party Management | Do you apply a cybersecurity due diligence process to validate the cybersecurity maturity of your partners/third parties before any interconnection? | Ad-hoc | 2 | Apply the Group's due diligence procedure and we are performing it on a new project. | Apply the Group's due diligence procedure and we are performing it on a new project. | 资讯安全盡職調查問卷_v1.0 https://drive.google.com/file/d/1Rbim8jpYhY8ZeVBL2pXTGLyW2YMuddAe/view?usp=share_link | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - List of the third parties and corresponding interconnection(s) - Deliverables - Third Party security assessment (before signing / renewing a contract) with validated interconnection(s), including but not limited to a remote access, a third party's device connectiing our network on site, site to site connection, application to application connection etc. - Deliverables - The records of remediation actions or accepted compensating mitigation messure of High/Medium risk associated to the third party. | 2023 | * Create the management document template | * IT Inventories third party * Third party assessment | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - List of the third parties and corresponding interconnection(s) - Deliverables - Third Party security assessment (before signing / renewing a contract) with validated interconnection(s), including but not limited to a remote access, a third party's device connectiing our network on site, site to site connection, application to application connection etc. - Deliverables - The records of remediation actions or accepted compensating mitigation messure of High/Medium risk associated to the third party. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 第三方列表和相应的互连 - 可交付成果 - 第三方安全评估（在签署 /更新合同之前）具有经过验证的互连，包括但不限于远程访问，第三方的设备连接我们的网站，网站连接到网站连接，应用程序连接，应用程序连接应用程序连接ETC。 - 可交付成果 - 补救措施的记录或公认的补偿措施减轻与第三方相关的高/中等风险的记录。 | * Create information security management documents, cover the required content. * If there is an network with a third party, a security assessment will be performed and the problems discovered are rectified | * 创建信息安全管理文件，涵盖所要求的内容。 * 如果与第三方有网络互联，则对其进行安全评估，并对发现的问题进行整改 | [7 empty] | 1 | 0
CY-IT201 | Protect | Secure management of the information system | Do you apply a patch management process and do you manage the obsolescence of your equipment (servers, workstations, firewalls, switches, VPN concentrators, mobile devices, etc.) and your applications? | Defined | 3 | 文檔 | document | https://glpi.tahoho.com.tw/ https://docs.google.com/document/d/1doFBE_4ryvKAwPMzcsYAijsN5PhTH3UB/edit?usp=share_link&ouid=112652071405849358717&rtpof=true&sd=true | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The tools or records maintaining the patching status of the equipment (should cover servers, workstations, network and security appliance and mobile devices when applicable,) and the applications, including the obsolescent one. - Deliverbables - Record of remediation actions or accepted compensating migtation mesuares to unresolvable vulnerabiities including obsolescent assets and application that are still in use. | 2024 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The tools or records maintaining the patching status of the equipment (should cover servers, workstations, network and security appliance and mobile devices when applicable,) and the applications, including the obsolescent one. - Deliverbables - Record of remediation actions or accepted compensating migtation mesuares to unresolvable vulnerabiities including obsolescent assets and application that are still in use. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 维护设备修补状态的工具或记录（应涵盖服务器，工作站，网络和安全设备以及适用的移动设备）以及包括过时的应用程序。 - 送货服务 - 修复措施的记录或接受的补偿中的中间人，包括仍在使用的过时资产和应用程序，包括无法解决的漏洞。 | * Create information security management documents, cover the required content. * Implement patch management and operation in accordance with the information security policy * Rectify the hidden dangers discovered | * 创建信息安全管理文件，涵盖所要求的内容。 * 按照信息安全政策实施补丁管理和操作 * 对发现的安全隐患做整改 | [7 empty] | 1 | 0
CY-IT202 | Protect | Logins and passwords management | Do you have a dedicated process for account and password management? Do you prevent the use of weak passwords? Is this policy enforced across your entire perimeter? | Defined | 3 | 流程控管 | Process control | https://docs.google.com/document/d/1ZWe0zeoO6AcEu8vF4qwuQy8hlFDIlJ7m/edit?usp=share_link&ouid=112652071405849358717&rtpof=true&sd=true | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The account lifecycle management is integrated with the HR employee management procedures of on joiner, mover and leaver (JML) - Deliverables - The accounts review with the business owners every 6 months. - Deliverables (IT only) - The password policy is deployed in the systems (Servers & workstations) and the applications, which is compliant with the Group password policy. | 2023 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The account lifecycle management is integrated with the HR employee management procedures of on joiner, mover and leaver (JML) - Deliverables - The accounts review with the business owners every 6 months. - Deliverables (IT only) - The password policy is deployed in the systems (Servers & workstations) and the applications, which is compliant with the Group password policy. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 帐户生命周期管理与人力资源雇员管理程序（JML）的人力资源员工管理程序（JML）集成在一起 - 可交付成果 - 每6个月与企业主进行审查。 - 可交付成果（仅此） - 密码策略被部署在系统（服务器和工作站）和应用程序中，该应用程序符合组密码策略。 | * Create information security management documents, cover the required content. * Perform the life cycle management of the account, and conduct a review of the account every 6 months * Implement the group's password security strategy | * 创建信息安全管理文件，涵盖所要求的内容。 * 进行账户的生命周期管理，并且每6个月对账户进行一次审查 * 实施集团的密码安全策略 | [7 empty] | 1 | 0
CY-IT203 | Protect | Access Control and Authentication | Regarding the services exposed on the Internet, does the authentication take place with the Google account and only with a strong authentication process? | Defined | 3 | MFA，LDAP | MFA, LDAP | https://drive.google.com/file/d/1Rbim8jpYhY8ZeVBL2pXTGLyW2YMuddAe/view?usp=share_link | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The list of the systems and services exposed on the Internet with the authentication type. - Deliverables - 2FA is deployed to all Google accounts - Deliverables - The Google SSO is applied to the access of the system (PaaS, IaaS, servers, workstations, appliance management, etc.) and the applications (SaaS) when applicable. Otherwise, a strong alternative SSO with 2FA is applied. | 2023 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The list of the systems and services exposed on the Internet with the authentication type. - Deliverables - 2FA is deployed to all Google accounts - Deliverables - The Google SSO is applied to the access of the system (PaaS, IaaS, servers, workstations, appliance management, etc.) and the applications (SaaS) when applicable. Otherwise, a strong alternative SSO with 2FA is applied. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 具有身份验证类型在Internet上公开的系统和服务列表。 - 可交付成果-2FA部署到所有Google帐户 - 可交付成果 - Google SSO适用于系统（PAAS，IAAS，服务器，工作站，设备管理等）和应用程序（SaaS）（SAAS）的访问。否则，将应用具有2FA的强替代SSO。 | * Create information security management documents, cover the required content. * Timely updating the list of Internet assets in time * Google account must have a secondary verification of logging in * If possible, deploy Google's single login | * 创建信息安全管理文件，涵盖所要求的内容。 * 及时更新互联网资产清单 * 谷歌账户必须有登录的二次验证 * 如可能，部署谷歌的单点登录 | [7 empty] | 1 | 0
CY-IT204 | Protect | Access Control and Authentication | Do you use an authentication directory for the IT perimeter and run regular audits with the AD Analyzer tool? | Defined | 3 | We performed the AD analyzer and validate the user accounts regularly | We performed the AD analyzer and validate the user accounts regularly | https://drive.google.com/file/d/1hD_xrd330-Dhpth1JjeDVYZpoL8N5sk4/view?usp=share_link https://docs.google.com/spreadsheets/d/1CzxfZtInt47KtaLfPsgnNLrLTcHMlL2t/edit?usp=share_link&ouid=112652071405849358717&rtpof=true&sd=true | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The deployed authentication master list - Deliverables - The updated AD Analyzer report when AD available - Deliverables - The remediation actions of the AD Analyzer report when AD available | 2023 | * Create the management document template * Asia CSEC team conducts the running of AD Analyzer | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The deployed authentication master list - Deliverables - The updated AD Analyzer report when AD available - Deliverables - The remediation actions of the AD Analyzer report when AD available | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 部署的身份验证主列表 - 可交付成果 - 更新的广告分析仪报告可用广告 - 可交付成果 - 广告可用时广告分析仪报告的补救措施 | * Create information security management documents, cover the required content. * Timely update account list of identity authentication * If there is an AD domain control server, there is a configuration change in the AD domain control server. Use the Ad Analyzer tool to scan and rectify the problems found | * 创建信息安全管理文件，涵盖所要求的内容。 * 及时更新进行身份认证的账户清单 * 如果有AD域控服务器，在AD域控服务器有配置变更是，使用AD Analyzer工具进行扫描，并对发现的问题进行整改 | [7 empty] | 1 | 0
CY-IT205 | Protect | Access Control and Authentication | Do you use the AD's three-tier model? | Defined | 3 | We performed the AD analyzer ad fix the found issues | We performed the AD analyzer ad fix the found issues | https://ada.cogiceo.com/veolia/login | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The deployment of the AD's three-tier model, which has 3 tiers (AD domain admin, application/server admin and client/workstation support) and jump server for each tier. | 2024 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The deployment of the AD's three-tier model, which has 3 tiers (AD domain admin, application/server admin and client/workstation support) and jump server for each tier. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 广告的三层模型的部署，该模型具有3层（AD域管理员，Application/Server Admin和Client/WorkStation支持）和每个层的跳转服务器。 | * Create information security management documents, cover the required content. * If there is an AD domain control server, the AD domain shall be deployed in accordance with the three -layer security model (AD domain administrator, Application/Server ADmin and Client/WORKSTATATION) and springboards at each layer. | * 创建信息安全管理文件，涵盖所要求的内容。 * 如果有AD域控服务器，AD域要按照三层安全模型部署（AD域管理员，Application/Server Admin和Client/WorkStation支持）和每个层的跳板机。 | 1. to use a jump server (or admin workstation) for the server access 2. In case of AD forest or multiple AD domains, a domain admin cannot manage other domains. | [6 empty] | 1 | 0
CY-IT206 | Protect | Network | Do you have an inventory of Internet access points (IAPs)? Have you implemented a secure exit architecture to the Internet? | Defined | 3 | We have the inventory list | We have the inventory list | https://drive.google.com/file/d/1yJ40yC2tmKizmi1IU52FEOHMfcLB6mkG/view?usp=share_link https://drive.google.com/file/d/1g5WEWFslpGMxXKSCmBD3c35X6C3W8r9S/view?usp=share_link | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The updated network architecture of the Internet access points with the data flow matrix remark, including the networks on premis and clouds (like GCP, AWS etc.) - Deliverables - A security solution of the Internet access is deployed at both network (firewall) and application (web proxy or web security agent) level. | 2023 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The updated network architecture of the Internet access points with the data flow matrix remark, including the networks on premis and clouds (like GCP, AWS etc.) - Deliverables - A security solution of the Internet access is deployed at both network (firewall) and application (web proxy or web security agent) level. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 具有数据流矩阵备注的Internet访问点的更新网络体系结构，包括Premis和Clouds上的网络（例如GCP，AWS等） - 可交付成果 - 网络（防火墙）和应用程序（Web代理或Web Security Agent）级别部署了Internet访问的安全解决方案。 | * Create information security management documents, cover the required content. * Update the network topology in time and mark the data stream * Deploy firewalls on the network layer, apply the application of firewalls (applicable), Internet access agent, etc. | * 创建信息安全管理文件，涵盖所要求的内容。 * 及时更新网络拓扑图，并标注数据流 * 在网络层部署防火墙，应用层部署应用防火墙（如适用），互联网访问代理等 | Describe the security settings for the internet access | [6 empty] | 1 | 0
CY-IT207 | Protect | Network | Do you have a network architecture document presenting your information system? Have you segmented your information system by setting up a separation between each zone? Are there interconnections between the IT and the OT if there is an industrial information system in your area? | Defined | 3 | We have updated network diagram | We have updated network diagram | https://drive.google.com/file/d/1g5WEWFslpGMxXKSCmBD3c35X6C3W8r9S/view?usp=share_link https://drive.google.com/file/d/1g5WEWFslpGMxXKSCmBD3c35X6C3W8r9S/view?usp=share_link | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The updated network diagram with the interconnection between IT and OT (when applicable), the data flow and the security control. - Deliverables - The new set up and the update of the network architecture, firewall security policy etc are validated by the BU cyber security team or the cyber security correspondent. - Deliverables - The network segments with ACL are deployed following the Group standard. | 2024 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The updated network diagram with the interconnection between IT and OT (when applicable), the data flow and the security control. - Deliverables - The new set up and the update of the network architecture, firewall security policy etc are validated by the BU cyber security team or the cyber security correspondent. - Deliverables - The network segments with ACL are deployed following the Group standard. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 具有IT与OT之间互连的更新网络图（如果适用），数据流和安全控制。 - 可交付成果 - 新设置和网络体系结构，防火墙安全策略等的更新由BU网络安全团队或网络安全通讯员验证。 - 可交付成果 - 具有ACL的网络段按照组标准部署。 | * Create information security management documents, cover the required content. * Update the topology map in time, including the security equipment and communication between the office network and the industrial control network * Change of security strategies must be reviewed by information security officials * Deploy the network according to the group's network security architecture model | * 创建信息安全管理文件，涵盖所要求的内容。 * 及时更新完了拓扑图，含办公网络和工控网络之间的安全设备和通讯 * 安全策略的变更须经信息安全官审核 * 按照集团的网络安全架构模型部署网络 | [7 empty] | 1 | 0
CY-IT208 | Protect | Network | Do you have a list of assets exposed on the Internet? Do you patch these assets on a regular basis? Do you have the VMDR agent (Qualys) installed on these assets? Do you have a dedicated security watch on these assets? Do you assess the criticality of assets exposed on the Internet? | Defined | 3 | We have the inventory list | We have the inventory list | https://drive.google.com/file/d/1yJ40yC2tmKizmi1IU52FEOHMfcLB6mkG/view?usp=share_link | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The list of the Internet exposed assets with Criticality - Deliverables - Patch the Internet exposed assets in time - Deliverables - Deploy the VMDR agent (Qualys) on the Internet exposed assets when applicable. - Deliverables - Monitor and protect of the Internet exposed assets by using the vulnerability scan, Web security Scan and EDR etc - Deliverables - In case of some issues found due to above actions, the remediation actions will be performed | 2023 | * Create the management document template * Asia CSEC team conducts the deployment of Qualys Cloud Agent | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The list of the Internet exposed assets with Criticality - Deliverables - Patch the Internet exposed assets in time - Deliverables - Deploy the VMDR agent (Qualys) on the Internet exposed assets when applicable. - Deliverables - Monitor and protect of the Internet exposed assets by using the vulnerability scan, Web security Scan and EDR etc - Deliverables - In case of some issues found due to above actions, the remediation actions will be performed | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 关键的Internet暴露资产列表 - 可交付成果 - 及时修补Internet暴露资产 - 可交付成果 - 适用时在Internet暴露资产上部署VMDR代理（Qualys）。 - 可交付成果 - 使用漏洞扫描，网络安全扫描和EDR等监视和保护Internet暴露资产 - 可交付成果 - 如果由于上述操作而发现的某些问题，将执行补救措施 | * Create information security management documents, cover the required content. * Timely updating the list of Internet assets in time * Deploy VMDR agents, find safety problems, and repairs timely repair | * 创建信息安全管理文件，涵盖所要求的内容。 * 及时更新互联网资产清单 * 部署VMDR代理，发现安全问题，及时修复 | Remark the internet exposed assets and critical assets Patch update VMDR deployment | [6 empty] | 1 | 0
CY-IT209 | Protect | Integration of security in projects | Is cybersecurity integrated at each key stage of IT projects (expression of needs, definition of the architecture, validation before going into production) ? | Ad-hoc | 2 | Involve cyber security for information system validation | Involve cyber security for information system validation | https://drive.google.com/file/d/1kkGYq-Mg1IhagavmfMHQKjjNcqIyXXaj/view?usp=share_link | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The master list of the cyber security validation for IT/OT projects and Service Contracts. - Deliverables - The cyber security assessment (Secure by Design) during the stages of design, developemnt go-live and significant changes or update of IT/OT projects and Services. - Deliverables - The records of Remediation action for security findings. - Deliverables - Third Party Security Assessment for suppliers. (Supplier Background and maturity) | 2023 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The master list of the cyber security validation for IT/OT projects and Service Contracts. - Deliverables - The cyber security assessment (Secure by Design) during the stages of design, developemnt go-live and significant changes or update of IT/OT projects and Services. - Deliverables - The records of Remediation action for security findings. - Deliverables - Third Party Security Assessment for suppliers. (Supplier Background and maturity) | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - IT/OT项目和服务合同的网络安全验证的主列表。 - 可交付成果 - 设计阶段的网络安全评估（按设计安全），开发eNSEMNT -LIVE和重大更改或更新IT/OT项目和服务。 - 可交付成果 - 安全发现的补救措施记录。 - 可交付成果 - 第三方安全评估供应商。 （供应商背景和成熟） | * Create information security management documents, cover the required content. * Add information security clauses to the supplier contract, and make annual security assessment of the supplier * Make security assessment of the information system (three stages: design, implementation and operation), repair security issues | * 创建信息安全管理文件，涵盖所要求的内容。 * 在供应商合同中添加信息安全条款，并对供应商做每年的安全评估 * 对信息系统进行安全评估（三个阶段：设计，实施和运营），修复安全问题 | Involve cyber security for information system validation | [6 empty] | 1 | 0
CY-IT210 | Protect | Awareness and training | Do you have an awareness program and do you conduct regular cybersecurity awareness training for your employees? | Defined | 3 | We plan the training and deliver it | We plan the training and deliver it | https://docs.google.com/spreadsheets/d/1OrJoAJph1ZPr5eJh9u3VfFUDZXctjGEh/edit?usp=share_link&ouid=112652071405849358717&rtpof=true&sd=true https://docs.google.com/spreadsheets/d/1G_J6m3ajGiErhIJA0C4vEJ_2DWSdJYtF/edit?usp=share_link&ouid=112652071405849358717&rtpof=true&sd=true | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The user awareness training with report, communicating with the management annually. Training should be delivered by online or physical class in person with attendance records. - Deliverables - The phishing simulation test with report, communicating with the management annually. | 2023 | * Create the management document template * Launch the user awareness training campaign and the simulated phishing test periodically | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The user awareness training with report, communicating with the management annually. Training should be delivered by online or physical class in person with attendance records. - Deliverables - The phishing simulation test with report, communicating with the management annually. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 用户意识培训通过报告，每年与管理层进行沟通。培训应由出勤记录的在线或实体课程进行。 - 可交付成果 - 带有报告的网络钓鱼模拟测试，每年与管理层进行通信。 | * Create information security management documents, cover the required content. * Follow the arrangement of the information security department of the Chinese headquarters to conduct user security training and fishing test. For personnel with unqualified training and fishing tests, arrange re -training and testing. | * 创建信息安全管理文件，涵盖所要求的内容。 * 跟随中国总部信息安全部门的安排，进行用户安全培训，以及钓鱼测试。对于培训和钓鱼测试不合格的人员安排再培训和测试。 | [7 empty] | 1 | 0
CY-IT211 | Protect | Server hardening | Do you put in place a hardening of the domain controllers and servers? | Defined | 3 | yes | yes | https://drive.google.com/file/d/1hD_xrd330-Dhpth1JjeDVYZpoL8N5sk4/view?usp=share_link | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The deployment of the System hardening configuration following Group system hardening policy. - Deliverables (IT only) - The implementation of the AD security configuration following the Group AD Security Policy (When AD is applicable). - Deliverables - The review and update of security hardening annually. - Deliverables - The record of the exception handling/control with approval. | 2024 | * Create the management document template | * windows hardening | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The deployment of the System hardening configuration following Group system hardening policy. - Deliverables (IT only) - The implementation of the AD security configuration following the Group AD Security Policy (When AD is applicable). - Deliverables - The review and update of security hardening annually. - Deliverables - The record of the exception handling/control with approval. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 组系统硬化策略之后的系统硬化配置的部署。 - 可交付成果（仅） - 集体广告安全策略之后的广告安全配置的实现（AD适用时）。 - 可交付成果 - 每年对安全性硬化的审查和更新。 - 可交付成果 - 经批准的异常处理/控制的记录。 | * Create information security management documents, cover the required content. * Safety reinforcement of server and AD domain control (if any) is based on information security policy, including but not limited to patch renewal, virus protection, deployment EDR * If you have AD domain control, do AD security analysis, and eliminate hidden dangers * Rectify the risk discovered | * 创建信息安全管理文件，涵盖所要求的内容。 * 按照信息安全政策对服务器和AD域控（如果有）进行安全加固，包括但不限于补丁更新、病毒防护、部署EDR * 如果有AD域控，做AD安全分析，并消除隐患 * 对发现的风险进行整改 | 1. Defined process for Configuration hardening to workstations. 2. Defined role to handle the configuration hardening. 3. Regularly monitor and update the the hardening control to most of the workstations. 4. Review the configraution hardening standard annually. 5. Exception approval and handling / record keeping | [6 empty] | 1 | 0
CY-IT212 | Protect | Dedicated accounts for administration | Are administration tasks only performed from a dedicated account? | Defined | 3 | 需使用特定-管理帳號 | Requires a specific administrator account | https://drive.google.com/file/d/1qCfHRP_jEKlo0ndYAb3guzWV64clmuv5/view?usp=share_link | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The Master list of the Applications / System privileged accounts with the Role(s)-based assignment to the responsible people - Deliverables - The administration tasks are only performed by privileged accounts / Role(s). - Deliverables - The privilege accounts (Eg. Administrators or sensitive data access) are separated with the normal user accounts and should be applied with 2FA. - Deliverables - The administrative access only through the Jump host (Exclude SaaS) - Deliverbales - The admin accounts should be reviewed regularly. | 2023 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The Master list of the Applications / System privileged accounts with the Role(s)-based assignment to the responsible people - Deliverables - The administration tasks are only performed by privileged accounts / Role(s). - Deliverables - The privilege accounts (Eg. Administrators or sensitive data access) are separated with the normal user accounts and should be applied with 2FA. - Deliverables - The administrative access only through the Jump host (Exclude SaaS) - Deliverbales - The admin accounts should be reviewed regularly. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 应用程序 /系统特权帐户的主列表，其基于角色的作业给负责人 - 可交付成果 - 管理任务仅由特权帐户 /角色执行。 - 可交付成果 - 特权帐户（例如管理员或敏感数据访问）与普通用户帐户分开，应使用2FA应用。 - 可交付成果 - 仅通过跳跃主机（排除SaaS）的管理访问 - 可交付成果 - 管理员帐户应定期审查。 | * Create information security management documents, cover the required content. * Timely update the list of applications /system privileges accounts and regular review * Separate privilege accounts and ordinary user accounts, and secondary login certification should be used. * Install a springboard to access the server | * 创建信息安全管理文件，涵盖所要求的内容。 * 及时更新应用程序 /系统特权帐户清单，并定期审查 * 分开特权帐户与普通用户帐户，应使用二次登录认证。 * 安装跳板机访问服务器 | [7 empty] | 1 | 0
CY-IT213 | Protect | Mobile devices | Is a mobile device security policy implemented? | Ad-hoc | 2 | 特權帳號，有使用雙重驗證(手機端) | This privileged account uses two-factor authentication (mobile version). | https://drive.google.com/file/d/1Rbim8jpYhY8ZeVBL2pXTGLyW2YMuddAe/view?usp=share_link | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The inventory of the active company owned mobile device or BYOD when applicable - Deliverables - The MDM deployment on the mobile devices. - Deliverables - The security policies and configuration are enforcement for accessing Veolia resources with mobile applications | 2023 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The inventory of the active company owned mobile device or BYOD when applicable - Deliverables - The MDM deployment on the mobile devices. - Deliverables - The security policies and configuration are enforcement for accessing Veolia resources with mobile applications | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 现有的活动公司拥有的移动设备或BYOD的库存 - 可交付成果 - 移动设备上的MDM部署。 - 可交付成果 - 安全策略和配置是用于使用移动应用程序访问Veolia资源的执行 | * Create information security management documents, cover the required content. * Update the mobile device (owned by the company) or your own equipment orders in a timely manner * Deploy MDM on mobile devices, and forcibly implement security strategies and configurations | * 创建信息安全管理文件，涵盖所要求的内容。 * 及时更新移动设备（公司所有的）或自带设备订单 * 在移动设备上部署MDM，并强制实施安全策略和配置 | [7 empty] | 1 | 0
CY-IT214 | Protect | Classification and data protection | Is there a policy for classification and protection of data and associated processes? Do you apply a different level of security for different types of data (more or less sensitive)? | Ad-hoc | 2 | We evaluate the data security | We evaluate the data security | https://docs.google.com/document/d/1xT5ufiy8R298HfBOV_tEjCU5JSw9glT9/edit?usp=share_link&ouid=112652071405849358717&rtpof=true&sd=true | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The updated inventory of Confidential, sensitive and Personal Data with Data Controller info. - Deliverables - The data protection measures and associated processes are deployed to Confidential, sensitive and Personal Data based on the data classification - Deliverbales - Data Retension policy applied to Confidential, sensitive and Personal Data. - Deliverables - Data Labeling applied to Confidential, sensitive and Personal Data | 2024 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The updated inventory of Confidential, sensitive and Personal Data with Data Controller info. - Deliverables - The data protection measures and associated processes are deployed to Confidential, sensitive and Personal Data based on the data classification - Deliverbales - Data Retension policy applied to Confidential, sensitive and Personal Data. - Deliverables - Data Labeling applied to Confidential, sensitive and Personal Data | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 具有数据控制器信息的机密，敏感和个人数据的更新清单。 - 可交付成果 - 基于数据分类将数据保护措施和相关流程部署到机密，敏感和个人数据 -DeliverBales-应用于机密，敏感和个人数据的数据retension策略。 - 可交付成果 - 应用于机密，敏感和个人数据的数据标签 | * Create information security management documents, cover the required content. * Classification of data: confidential, sensitive and personal data, and update the list of asset classification in a timely manner. * Implement corresponding security protection measures based on data classification, and comply with data retention requirements | * 创建信息安全管理文件，涵盖所要求的内容。 * 对数据进行分类：机密，敏感和个人数据，及时更新资产分类清单。 * 基于数据分类实施相应的安全保护措施，并遵守数据保留要求 | [7 empty] | 1 | 0
CY-IT215 | Protect | Device encryption | Are your laptops and mobile devices (phones, tablets, etc.) encrypted? (A Chromebook is encrypted by default). | Ad-hoc | 2 | Encript the device if having confidential data | Encript the device if having confidential data | https://docs.google.com/document/d/1doFBE_4ryvKAwPMzcsYAijsN5PhTH3UB/edit?usp=share_link&ouid=112652071405849358717&rtpof=true&sd=true | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - OS Encryption enforcement from MDM policy to laptops, mobile devices including BYOD. - Deliverables - The encryption deployment on the laptops and the mobile devices. (Unmanaged devices) | 2024 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - OS Encryption enforcement from MDM policy to laptops, mobile devices including BYOD. - Deliverables - The encryption deployment on the laptops and the mobile devices. (Unmanaged devices) | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 从MDM策略到笔记本电脑，包括BYOD在内的移动设备的OS加密执行。 - 可交付成果 - 笔记本电脑和移动设备上的加密部署。 （不受管理的设备） | * Create information security management documents, cover the required content. * Encrypt the data on the mobile device | * 创建信息安全管理文件，涵盖所要求的内容。 * 对移动设备上的数据进行加密 | [7 empty] | 1 | 0
CY-IT301 | Detect | Deployment of detection tools | Are the following tools deployed throughout your perimeter? - Antivirus, - Endpoint Detection Response (EDR), - Compliance, - Qualys Agent, - AD Blacklist. Specify in the comments if other tools have been deployed. | Defined | 3 | 目前已安裝EDR及進行Qualys掃描 | EDR has been installed and a Qualys scan has been performed. | https://drive.google.com/file/d/1ozrf7LJyAqvqiy9LiB_ouCYvRjj0-bDH/view?usp=share_link https://drive.google.com/file/d/10CbPWDkZTVqzKwAUVrJHkbkl9p5gNJvq/view?usp=share_link | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - Extract KPI report from the Group‘s KPI dashboard - Deliverables - The deployment of the Compliance tool with list of active devices. - Deliverables - The deployment of the EDR with list of active devices. - Deliverables - The deployment of the antivirus with list of active devices. - Deliverables - The deployment of the Qualys Agent with list of active devices. - Deliverables - The deployment of the AD Blacklist with active configuration. Specify if other tools have been deployed. | 2023 | * Create the management document template * Asia CSEC team conducts and supports the security tool deployment | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - Extract KPI report from the Group‘s KPI dashboard - Deliverables - The deployment of the Compliance tool with list of active devices. - Deliverables - The deployment of the EDR with list of active devices. - Deliverables - The deployment of the antivirus with list of active devices. - Deliverables - The deployment of the Qualys Agent with list of active devices. - Deliverables - The deployment of the AD Blacklist with active configuration. Specify if other tools have been deployed. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 从组的KPI仪表板提取KPI报告 - 可交付成果 - 通过活动设备列表的合规工具的部署。 - 可交付成果 - EDR的部署以及有效设备列表。 - 可交付成果 - 使用活动设备列表的防病毒软件部署。 - 可交付成果 - 使用活动设备列表的Qualys代理部署。 - 可交付成果 - 通过主动配置的AD黑名单的部署。 指定是否部署了其他工具。 | * Create information security management documents, cover the required content. * Use the group's instrument panel management performance * Deployment compliance tool * Deploy EDR * Deploy anti -virus software * Deploy AD password blacklist * Deploy QUALYS cloud agent * Other safety tools that require deployment | * 创建信息安全管理文件，涵盖所要求的内容。 * 使用集团仪表盘管理绩效 * 部署合规工具 * 部署EDR * 部署防病毒软件 * 部署AD密码黑名单 * 部署Qualys云代理 * 其它要求部署的安全工具 | [7 empty] | 1 | 0
CY-IT302 | Detect | Audits, tests, and vulnerability detection | Do you perform vulnerability scans on a regular basis (at least every month) and do you apply the remediation actions identified as a result? | Defined | 3 | 每月進行Qualys掃描 | Qualys scans are performed monthly. | https://drive.google.com/file/d/10CbPWDkZTVqzKwAUVrJHkbkl9p5gNJvq/view?usp=share_link | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The list of the scanned assests - Deliverables - The list with records of the monthly vulnerability scans performed in last 18 months. - Deliverables - The records of remediation actions performed in last 18 months. | 2023 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The list of the scanned assests - Deliverables - The list with records of the monthly vulnerability scans performed in last 18 months. - Deliverables - The records of remediation actions performed in last 18 months. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 扫描的驴子清单 - 可交付成果 - 列表中有记录，记录了过去18个月内执行的每月漏洞扫描。 - 可交付成果 - 过去18个月内采取的补救措施记录。 | * Create information security management documents, cover the required content. * Timely update the list of assets of vulnerability scanning * Execute the vulnerability scan, keep the scanning record of the past August * If a vulnerability is found, it will be rectified and retains the rectification records over the past 18 months. | * 创建信息安全管理文件，涵盖所要求的内容。 * 及时更新漏洞扫描的资产清单 * 执行漏洞扫描，保留过去18月的漏扫记录 * 如发现漏洞，则进行整改，并保留过去18个月的整改记录。 | 1. Management documents of assets inventory and vulnerability scan 2. The vulnerability scan report 3. Remediation action plan and follow 4. Verify the remediation action result | [6 empty] | 1 | 0
CY-IT303 | Detect | Audits, tests, and vulnerability detection | Do you regularly (at least every 3 years) perform intrusion tests, audits and/or red teams and do you carry out the identified remediation actions resulting from them? | Defined | 3 | 每月進行Qualys掃描 | Qualys scans are performed monthly. | https://drive.google.com/file/d/10CbPWDkZTVqzKwAUVrJHkbkl9p5gNJvq/view?usp=share_link | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. Audit - Deliverables - The list of all audit campaigns performed in last 3 years. - Deliverables - The audit reports with scope, findings and follow up actions. - Deliverables - The records of remediation actions with the date of completion. Pentest / Red Teaming Exerciese - Deliverables - The list of all Pentest Campaigns with reports in last 3 years. - Deliverables - The Pentest reports with, scope, findings and follow up actions. - Deliverables - The records of remediation actions with the date of completion. | 2023 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. Audit - Deliverables - The list of all audit campaigns performed in last 3 years. - Deliverables - The audit reports with scope, findings and follow up actions. - Deliverables - The records of remediation actions with the date of completion. Pentest / Red Teaming Exerciese - Deliverables - The list of all Pentest Campaigns with reports in last 3 years. - Deliverables - The Pentest reports with, scope, findings and follow up actions. - Deliverables - The records of remediation actions with the date of completion. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 审计 - 可交付成果 - 过去3年内执行的所有审核活动列表。 - 可交付成果 - 审计报告，范围，调查结果和后续行动。 - 可交付成果 - 完成日期的补救措施记录。 五旬节 /红色团队练习 - 可交付成果 - 过去3年中所有五旬节活动的清单。 - 可交付成果 - 带有范围，调查结果和后续行动的五旬节报告。 - 可交付成果 - 完成日期的补救措施记录。 | * Create information security management documents, cover the required content. * A audit every 3 years, and record the audit results and rectification results * Carry out intrusion testing, and record the audit results and rectification results | * 创建信息安全管理文件，涵盖所要求的内容。 * 每3年进行一次审计，并记录审计结果和整改结果 * 进行入侵检测，并记录审计结果和整改结果 | 1. Management documents of audit and penetration test 2. The audit or the penetration test report 3. Remediation action plan and follow 4. Verify the remediation action result | [6 empty] | 1 | 0
CY-IT304 | Detect | Log management | Is a log management policy applied and updated regularly (every 2 years)? Are the logs sent to a central container (log well, etc.) ? | Ad-hoc | 2 | FW-已設定 AD-SSO | FW - AD-SSO already configured | https://drive.google.com/file/d/1dLzM420GlI5kzZgYlc5zE-SKUDbHBkoQ/view?usp=share_link | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The centralized logging with the corresponding log types listed in Group policy - Deliverables - The log retention is 6 months at least - Deliverables - The NTP is setup properly to ensure the log records with the accurate time stamp. - Deliverables - The Security monitoring and response. | 2024 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The centralized logging with the corresponding log types listed in Group policy - Deliverables - The log retention is 6 months at least - Deliverables - The NTP is setup properly to ensure the log records with the accurate time stamp. - Deliverables - The Security monitoring and response. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 集中日志记录，其中包含组策略中列出的相应日志类型 - 可交付成果 - 保留日志至少为6个月 - 可交付成果 - 正确设置NTP，以确保使用准确的时间戳的日志记录。 - 可交付成果 - 安全监控和响应。 | * Create information security management documents, cover the required content. * Reserve logs for at least 6 months * Configure NTP service, synchronize time * Timely analysis of the logs, if there are hidden safety hazards, take remedial measures in a timely manner | * 创建信息安全管理文件，涵盖所要求的内容。 * 保留日志至少6个月 * 配置NTP服务，同步时间 * 对日志进行及时分析，如有安全隐患，及时采取补救措施 | The log includes network device and application systems, not only firewall. And its retention should be 6 months | [6 empty] | 1 | 0
CY-IT401 | Respond | Incident Management | Do you apply the group cybersecurity incident management procedure? Do you have a local cybersecurity incident management procedure? Is this procedure updated and tested at least every 3 years during exercises? | Ad-hoc | 2 | DRP Plan 1.2022/10/19-runing table test | DRP Plan 1.2022/10/19-running table test | https://docs.google.com/document/d/19jhIWGYm7CHKUXAIL0zTQ4mHWt5xyE-z/edit?usp=share_link&ouid=112652071405849358717&rtpof=true&sd=true | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The updated Cyber Security incident escalation contacts. - Deliverables - The list of major cyber security incident records for last 18 months. - Deliverables - The major cyber security Incident handling reports when situation happened (Record kept for 18 months). | 2023 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The updated Cyber Security incident escalation contacts. - Deliverables - The list of major cyber security incident records for last 18 months. - Deliverables - The major cyber security Incident handling reports when situation happened (Record kept for 18 months). | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 更新的网络安全事件升级联系人。 - 可交付成果 - 过去18个月的主要网络安全事件记录列表。 - 可交付成果 - 发生情况时的主要网络安全事件处理报告（记录保存了18个月）。 | * Create information security management documents, cover the required content. * Operation according to the response process of the formulation of information security incidents. If necessary, do desktop exercises once a year. * If the information security incident occurs in time, cooperate with the headquarters to conduct information security incident surveys, and the system recovery. The information security incident report retains 18 months. | * 创建信息安全管理文件，涵盖所要求的内容。 * 按照制定的信息安全事件响应流程进行操作。如需要，每年做一次桌面演练。 * 如果发生信息安全事件及时上报，配合总部进行信息安全事件调查，系统恢复。信息安全事件报告保留18个月。 | [7 empty] | 1 | 0
CY-IT402 | Respond | Crisis Management | Do you use the group alert and crisis management procedure? Do you have a local crisis management procedure? Is this procedure regularly updated and tested during exercises? | Defined | 3 | We apply the incident and crisis management procedure, We had a case of Exchange server issue, which was fixed with support of the Group security team. | We apply the incident and crisis management procedure, We had a case of Exchange server issue, which was fixed with support of the Group security team. | https://docs.google.com/document/d/1_qedweDaDPjJ3ap7lpwWvb7gZpOEM5Bx/edit?usp=share_link&ouid=112652071405849358717&rtpof=true&sd=true | - People - Role(s) defined to manage the cyber security crisis - Process - Documented guide(s) or procedure(s) with scope for the cyber security crisis management - Deliverables - The updated local contact of crisis management team - Deliverables - The list of crisis records for last 18 months, - Deliverables - The crisis management report when crisis situation happened (Record kept for 18 months). | 2023 | * Create the management document template | N/A | - People - Role(s) defined to manage the cyber security crisis - Process - Documented guide(s) or procedure(s) with scope for the cyber security crisis management - Deliverables - The updated local contact of crisis management team - Deliverables - The list of crisis records for last 18 months, - Deliverables - The crisis management report when crisis situation happened (Record kept for 18 months). | - 人 - 定义用于管理网络安全危机的角色 - 流程 - 具有网络安全危机管理范围的记录指南或程序 - 可交付成果 - 危机管理团队更新的本地联系人 - 可交付成果 - 过去18个月的危机记录清单， - 可交付成果 - 发生危机情况时的危机管理报告（记录保存了18个月）。 | * Create information security management documents, cover the required content. * Operation according to the management process of the information security crisis formulated. If necessary, do desktop exercises once a year. * If the information security crisis occurs, report in time. The information security crisis report retains 18 months. | * 创建信息安全管理文件，涵盖所要求的内容。 * 按照制定的信息安全危机管理流程进行操作。如需要，每年做一次桌面演练。 * 如果发生信息安全危机事件及时上报。信息安全危机报告保留18个月。 | [7 empty] | 1 | 0
CY-IT501 | Recover | Backup and recovery | Are you able to quickly restore an application, a system or data within your entity, whether on premise or in the cloud? | Ad-hoc | 2 | Cloud backup & localhost Backup | Cloud backup & localhost Backup | https://drive.google.com/file/d/1AqZbhesEjoEWlEEdPbBJyTExIwnhQXJ6/view?usp=share_link | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The data backup and recovery plan - Deliverables - The data backup media are encrypted, stored securly and separated from the the source system. - Deliverables - The records of performing the recovery drill and validated regularly. - Deliverables - The data backup retention applied according to the Policy. - Deliverables - High Availablility and/or Disaster Recovery Plan for Critical application / systems meeting the SLA. | 2024 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The data backup and recovery plan - Deliverables - The data backup media are encrypted, stored securly and separated from the the source system. - Deliverables - The records of performing the recovery drill and validated regularly. - Deliverables - The data backup retention applied according to the Policy. - Deliverables - High Availablility and/or Disaster Recovery Plan for Critical application / systems meeting the SLA. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 数据备份和恢复计划 - 可交付成果 - 数据备份介质已加密，存储，并与源系统分开。 - 可交付成果 - 执行恢复训练并定期验证的记录。 - 可交付成果 - 根据政策应用的数据备份保留率。 - 可交付成果 - 针对SLA的关键应用程序 /系统的高可用性和 /或灾难恢复计划。 | * Create information security management documents, cover the required content. * According to business requirements, formulate data backup and recovery plans, and determine the retaining time of backup data. High reliability and disaster recovery plan meets business requirements. * Data backup medium needs to be encrypted, stored in different places (or stored-fire, waterproof, anti-theft) * At least once a system and data recovery drills each year, and verify its results. | * 创建信息安全管理文件，涵盖所要求的内容。 * 依据业务要求，制定数据备份和恢复计划，并确定备份数据的保留时长。高可靠性和灾难恢复计划要符合业务要求。 * 数据备份介质需要加密，异地存储（或在本地以安全方式存储-防火、防水、防盗） * 每年至少进行一次系统和数据恢复演练，并验证其结果。 | [7 empty] | 1 | 0
Detect | #REF! | #N/A | #N/A
Detect | 0 | #N/A | #N/A
Detect | #REF! | #N/A | #N/A
Detect | #REF! | #N/A | #REF!
Detect | #N/A | #N/A | #N/A
Detect | #N/A | #N/A | #N/A
Domain | Total Items | Total Score | Avg. Score
Domain | Total Items | Total Score | Avg. Score
Domain | Total Items | Total Score | Avg. Score
Domain | Total Number | Completed# | Completed %
Domain | Total Number | Completed# | Completed %
Domain | Total Number | Completed# | Completed %
Identify | #N/A | #N/A | #N/A
Identify | 0 | #N/A | #N/A
Identify | #REF! | #N/A | #N/A
Identify | #REF! | #N/A | #REF!
Identify | #N/A | #N/A | #N/A
Identify | #N/A | #N/A | #N/A
IT Assessment
IT Remediation Action Status
OT Assessment
OT Remediation Action Status
Overall Assessment
Overall Remediation Action Status
Protect | 0 | 0 | #DIV/0!
Protect | 11 | 29 | 2.64
Protect | #REF! | #N/A | #N/A
Protect | #N/A | #N/A | #N/A
Protect | #N/A | #N/A | #N/A
Protect | #N/A | #N/A | #N/A
Recover | #N/A | #N/A | #N/A
Recover | #REF! | 2 | #REF!
Recover | #REF! | #N/A | #N/A
Recover | #REF! | #N/A | #REF!
Recover | #N/A | #N/A | #N/A
Recover | #N/A | #N/A | #N/A
Respond | 0 | 0 | #DIV/0!
Respond | #REF! | 5 | #REF!
Respond | #REF! | #N/A | #N/A
Respond | 0 | 0 | 100%
Respond | #N/A | #N/A | #N/A
Respond | #N/A | #N/A | #N/A
Summary | #REF! | #N/A | #N/A
Summary | #REF! | #N/A | #N/A
Summary | #N/A | #N/A | #N/A
Total | #N/A | #N/A | #N/A
Total | #N/A | #N/A | #N/A
Total | #REF! | #N/A | #REF!

## Taho OT Remediation
OT Self Assessment | [23 empty] | @dropdown
Average
|  |  | Ad-hoc | 2.45 |  | Folder: 202209-Taiwan BU self-assessment
Internal Control Code | Domain | Sub-Domain | Maturity Level | Score | Comments | Document Link | Remediation Requirements | Year | Asia SCEC | Group Task Force | Maturity Lv. : Defined | Chinese Maturity Lv. : Defined | Remediation Plan | Chinese Remediation Plan | Action Plan | CAPEX (K Local Currency) | OPEX (K Local Currency ) | Responsible | Due Date | Status | Remediation Track | To do # | Completed #
CY-OT101 | Identify | Roles and Responsabilities | Defined | 3 | The document has been formulated, submitted and waiting for release | https://docs.google.com/document/d/1zUe3JQWBnb8q_kxQhNPl7utj-YS825K_/edit?usp=share_link&ouid=112652071405849358717&rtpof=true&sd=true | - People - The Chief Information Security Officer (CISO) or the Cyber Security Correspondent. Role(s) is defined to manage and be responsible to the cyber security functions. - Process - Documented scope and the cyber security function at BU/Project Level. - Deliverables - The job description of the CISO or the Cyber Security Correspondent. - Deliverables - The organization chart with the cyber security Role(s)/team at BU/Project Level and shared with Group/Zone CISOs. | 2023 | * Create the management document template | * The template (RACI)of the organization chart with the cyber security Role(s)/team | - People - The Chief Information Security Officer (CISO) or the Cyber Security Correspondent. Role(s) is defined to manage and be responsible to the cyber security functions. - Process - Documented scope and the cyber security function at BU/Project Level. - Deliverables - The job description of the CISO or the Cyber Security Correspondent. - Deliverables - The organization chart with the cyber security Role(s)/team at BU/Project Level and shared with Group/Zone CISOs. | - 人 - 首席信息安全官（CISO）或网络安全通讯员。角色被定义为管理和负责网络安全功能。 - 流程 - 在BU/项目级别记录的范围和网络安全功能。 - 可交付成果 - CISO或网络安全通讯员的职位描述。 - 可交付成果 - 具有网络安全角色/团队在BU/项目级别的组织图表，并与Group/Zone Cisos共享。 | * Create information security management documents, cover the required content. * Description of the person in charge of the person in charge of the industrial control information security * Organizational architecture of industrial control information security | * 创建信息安全管理文件，涵盖所要求的内容。 * 工控信息安全负责人的岗位职责描述 * 工控信息安全的组织架构图 | [7 empty] | 1 | 0
CY-OT102 | Identify | Budget | Defined | 3 | Have the cyber security budget every year | https://docs.google.com/spreadsheets/d/1fYyLbyJqcS9clGC6WKBIT4RoPqD7-b-wECRQQnEQrbo/edit#gid=609546198 | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - Cyber Security Budget Plan defined and submitted for approval (Following Group Standard Templated) - Deliverables - Security Action Plan covered in the budget plan which are endorsed by Group / Zone / BU CISO | 2023 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - Cyber Security Budget Plan defined and submitted for approval (Following Group Standard Templated) - Deliverables - Security Action Plan covered in the budget plan which are endorsed by Group / Zone / BU CISO | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 网络安全预算计划定义并提交批准（使用集团信息安全预算模板） - 可交付成果 - 预算计划中涵盖的安全行动计划，该计划由小组 /区域 / BU CISO认可 | * Create information security management documents, cover the required content. * Use the group's information security budget template to formulate budgets, and hand in management for approval | * 创建信息安全管理文件，涵盖所要求的内容。 * 使用集团信息安全预算模板制定预算，并交管理层审批 | [7 empty] | 1 | 0
CY-OT103 | Identify | Asset inventory | Ad-hoc | 2 | We have the udpated inventory | https://drive.google.com/file/d/1BOy4Rzxurm0wrNv5Hb_PbQPgkDSo39EQ/view?usp=share_link | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The updated list of physical assets. - Deliverables - The updated list of application assets. - Deliverables (IT only) - The asset catalog with the criticality defined. | 2023 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The updated list of physical assets. - Deliverables - The updated list of application assets. - Deliverables (IT only) - The asset catalog with the criticality defined. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 实际资产的更新列表。 - 可交付成果 - 更新的应用程序资产列表。 - 可交付成果（仅此） - 具有关键性定义的资产目录。 | * Create information security management documents, cover the required content. * According to the group's asset list template, update the asset list in time, in the asset list, you should mark whether it is an important asset, whether there is an Internet link, etc. | * 创建信息安全管理文件，涵盖所要求的内容。 * 按照集团资产清单模板及时更新资产清单记录，在资产清单中应该标注是否是重要资产、是否有互联网链接等 | [7 empty] | 1 | 0
CY-OT104 | Identify | Asset inventory | Defined | 3 | The assets security analysis is performed | https://docs.google.com/document/d/1xT5ufiy8R298HfBOV_tEjCU5JSw9glT9/edit?usp=share_link&ouid=112652071405849358717&rtpof=true&sd=true | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined.. - Deliverables - The updated list of criticality systems and applications (from Asset catalog) associated to contracts and Plants - Deliverables - Self-Assessment (BIA) on reviewing and identifying critical assets. | 2023 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined.. - Deliverables - The updated list of criticality systems and applications (from Asset catalog) associated to contracts and Plants - Deliverables - Self-Assessment (BIA) on reviewing and identifying critical assets. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 与合同和工厂相关的关键系统和应用程序（来自资产目录）的更新列表 - 可交付成果 - 自我评估（BIA），以审查和识别关键资产。 | * Create information security management documents, cover the required content. * Key asset list is updated in time (you can mark in the total asset list) * Evaluation of the impact of key assets for business (can be marked in the total asset list) | * 创建信息安全管理文件，涵盖所要求的内容。 * 关键资产清单及时更新（可以在总资产清单中做标注） * 对关键资产做业务影响度的评估（可以在总资产清单中做标注） | [7 empty] | 1 | 0
CY-OT105 | Identify | Audit & Control | Defined | 3 | Risk analysis is performed | https://docs.google.com/spreadsheets/d/1IQp2xAmWwMfKO05Z9OQhyZmZkoeCeoWe/edit?usp=share_link&ouid=112652071405849358717&rtpof=true&sd=true | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The cyber security self assessment (or audit) report with the remediation action plan at least once a year - Deliverables - The cyber security risk analysis report with the remediation action plan at least once a year - Deliverables - The records of remediation actions to the security findings from self-assessment (or Audit) and risk analysis report | 2023 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The cyber security self assessment (or audit) report with the remediation action plan at least once a year - Deliverables - The cyber security risk analysis report with the remediation action plan at least once a year - Deliverables - The records of remediation actions to the security findings from self-assessment (or Audit) and risk analysis report | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 网络安全自我评估（或审核）报告，每年至少每年一次进行补救行动计划 - 可交付成果 - 每年至少每年至少每年一次的网络安全风险分析报告 - 可交付成果 - 通过自我评估（或审计）和风险分析报告对安全发现的补救措施记录 | * Create information security management documents, cover the required content. * Do self -assessment once a year and rectify * Do the risk assessment once a year (the most risk items, 2 to 5), and rectify the rectification (The above two evaluations and rectification can be arranged together) | * 创建信息安全管理文件，涵盖所要求的内容。 * 每年做一次自评估，并整改 * 每年做一次风险评估（风险最高的项目，2至5个），并整改 （上述两项评估和整改可以安排一起做） | [7 empty] | 1 | 0
CY-OT202 | Protect | Acquisition of industrial equipment | Ad-hoc | 2 | validate cyber security for a system | https://docs.google.com/document/d/19GpKKMd97tSx6pjnJYOV2LL-RUjzg2rI/edit?usp=share_link&ouid=112652071405849358717&rtpof=true&sd=true | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The master list of the cyber security validation for IT/OT projects and Service Contracts. - Deliverables - The cyber security assessment (Secure by Design) during the stages of design, developemnt go-live and significant changes or update of IT/OT projects and Services. - Deliverables - The records of Remediation action for security findings. - Deliverables - Third Party Security Assessment for suppliers. (Supplier Background and maturity) | 2023 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The master list of the cyber security validation for IT/OT projects and Service Contracts. - Deliverables - The cyber security assessment (Secure by Design) during the stages of design, developemnt go-live and significant changes or update of IT/OT projects and Services. - Deliverables - The records of Remediation action for security findings. - Deliverables - Third Party Security Assessment for suppliers. (Supplier Background and maturity) | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - IT/OT项目和服务合同的网络安全验证的主列表。 - 可交付成果 - 从开发到实施的过程（全部或部分过程），对每个阶段做安全评估。 - 可交付成果 - 安全发现的补救措施记录。 - 可交付成果 - 第三方安全评估供应商。 （供应商背景和成熟） | * Create information security management documents, cover the required content. * In the contract signed with a third party, it must include information security clauses * If there is a system from development to implementation (all or part of the process), you need to do a security assessment at each stage * If you find hidden safety hazards, rectify rectification * Safety assessment of third parties every year | * 创建信息安全管理文件，涵盖所要求的内容。 * 在与第三方签署的合同中要包含信息安全条款 * 如果有系统从开发到实施的过程（全部或部分过程），需要在每个阶段做安全评估 * 如果发现安全隐患，要进行整改 * 每年对第三方进行安全评估 | [7 empty] | 1 | 0
CY-OT402 | Respond | Cybersecurity Incident & Crisis Management | Defined | 3 | Inciden management is applied. We had a case of Exchange server issue, which was fixed with support of the Group security team | https://docs.google.com/document/d/1_qedweDaDPjJ3ap7lpwWvb7gZpOEM5Bx/edit?usp=share_link&ouid=112652071405849358717&rtpof=true&sd=true | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The updated Cyber Security incident escalation contacts. - Deliverables - The list of major cyber security incident records for last 18 months. - Deliverables - The major cyber security Incident handling reports when situation happened (Record kept for 18 months). - People - Role(s) defined to manage the cyber security crisis - Process - Documented guide(s) or procedure(s) with scope for the cyber security crisis management - Deliverables - The updated local contact of crisis management team - Deliverables - The list of crisis records for last 18 months, - Deliverables - The crisis management report when crisis situation happened (Record kept for 18 months). | 2023 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The updated Cyber Security incident escalation contacts. - Deliverables - The list of major cyber security incident records for last 18 months. - Deliverables - The major cyber security Incident handling reports when situation happened (Record kept for 18 months). - People - Role(s) defined to manage the cyber security crisis - Process - Documented guide(s) or procedure(s) with scope for the cyber security crisis management - Deliverables - The updated local contact of crisis management team - Deliverables - The list of crisis records for last 18 months, - Deliverables - The crisis management report when crisis situation happened (Record kept for 18 months). | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 更新的网络安全事件升级联系人。 - 可交付成果 - 过去18个月的主要网络安全事件记录列表。 - 可交付成果 - 发生情况时的主要网络安全事件处理报告（记录保存了18个月）。 - 人 - 定义用于管理网络安全危机的角色 - 流程 - 具有网络安全危机管理范围的记录指南或程序 - 可交付成果 - 危机管理团队更新的本地联系人 - 可交付成果 - 过去18个月的危机记录清单， - 可交付成果 - 发生危机情况时的危机管理报告（记录保存了18个月）。 | * Create information security management documents, cover the required content. * Operation according to the response process and crisis management process formulated in the formulated information security incident. If necessary, do desktop exercises once a year. * If information security incidents (including crisis disposal) occur in time, and conduct information security incident investigations in cooperation with the headquarters, and system recovery. The information security incident report retains 18 months. | * 创建信息安全管理文件，涵盖所要求的内容。 * 按照制定的信息安全事件响应流程和危机管理流程进行操作。如需要，每年做一次桌面演练。 * 如果发生信息安全事件（含危机处置）及时上报，配合总部进行信息安全事件调查，系统恢复。信息安全事件报告保留18个月。 | [7 empty] | 1 | 0
CY-OT301 | Detect | Specification phase | Ad-hoc | 2 | Involve cyber security validation for the OT system | https://docs.google.com/spreadsheets/d/1IQp2xAmWwMfKO05Z9OQhyZmZkoeCeoWe/edit?usp=share_link&ouid=112652071405849358717&rtpof=true&sd=true | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The list of the cyber security validation for OT systems - Deliverables - The cyber security assessment during the stages of design, developemnt and go-live in OT systems. The cyber security assessment of the changes of the exisitng OT systems and applications - Deliverables - Records of remediation action when findings are available. | 2024 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The list of the cyber security validation for OT systems - Deliverables - The cyber security assessment during the stages of design, developemnt and go-live in OT systems. The cyber security assessment of the changes of the exisitng OT systems and applications - Deliverables - Records of remediation action when findings are available. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - OT系统的网络安全验证列表 - 可交付成果 - 设计阶段的网络安全评估，在OT系统中开发和live。对Exisitng OT系统和应用的更改的网络安全评估 - 可交付成果 - 可用发现时的补救措施记录。 | * Create information security management documents, cover the required content. * Create and use industrial control information security audit project templates (the Chinese headquarters security team provides templates), and the review list of all industrial control systems * Establish an information security audit process for the transformation of the industrial control system, and record the information security audit records at all stages of design, implementation, and operation and maintenance. * If there are rectification requirements after review, rectification and record rectification results. | * 创建信息安全管理文件，涵盖所要求的内容。 * 创建并使用工控信息安全审核项目模板（中国总部安全团队提供模板），以及所有工控系统的审核清单 * 建立工控系统改造的信息安全审核流程，并记录在设计，实施，运维各个阶段的信息安全审核记录。 * 如果审核后有整改要求，进行整改，并记录整改结果。 | [7 empty] | 1 | 0
CY-OT201 | Protect | Training & Awareness Raising | Defined | 3 | deliver the training | https://docs.google.com/spreadsheets/d/1OrJoAJph1ZPr5eJh9u3VfFUDZXctjGEh/edit?usp=share_link&ouid=112652071405849358717&rtpof=true&sd=true https://docs.google.com/spreadsheets/d/1G_J6m3ajGiErhIJA0C4vEJ_2DWSdJYtF/edit?usp=share_link&ouid=112652071405849358717&rtpof=true&sd=true | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The user awareness training with report, communicating with the management annually. Training should be delivered by online or physical class in person with attendance records. - Deliverables - The phishing simulation test with report, communicating with the management annually. | 2024 | * Create the management document template * Launch the user awareness training campaign and the simulated phishing test periodically | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The user awareness training with report, communicating with the management annually. Training should be delivered by online or physical class in person with attendance records. - Deliverables - The phishing simulation test with report, communicating with the management annually. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 用户意识培训通过报告，每年与管理层进行沟通。培训应由出勤记录的在线或实体课程进行。 - 可交付成果 - 带有报告的网络钓鱼模拟测试，每年与管理层进行通信。 | * Create information security management documents, cover the required content. * Follow the arrangement of the information security department of the Chinese headquarters to conduct user security training and fishing test. For personnel with unqualified training and fishing tests, arrange re -training and testing. | * 创建信息安全管理文件，涵盖所要求的内容。 * 跟随中国总部信息安全部门的安排，进行用户安全培训，以及钓鱼测试。对于培训和钓鱼测试不合格的人员安排再培训和测试。 | [7 empty] | 1 | 0
CY-OT206 | Protect | Workstations | Defined | 3 | Not Use USB |  | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The proof of technology restricting the use of removable storage - Deliverables - The proof of technology performing security scan before accessing removable storage | 2024 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The proof of technology restricting the use of removable storage - Deliverables - The proof of technology performing security scan before accessing removable storage | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 限制使用可移动存储的技术证明 - 可交付成果 - 在访问可移动存储之前进行安全扫描的技术证明 | * Create information security management documents, cover the required content. * It is forbidden to unnecessary USB connection * If you use USB due to business needs, you can do a security inspection of USB according to the information security management specifications, and then use it | * 创建信息安全管理文件，涵盖所要求的内容。 * 禁止不必要的USB连接 * 如果因业务需要，而使用USB，则按照信息安全管理规范先对USB做安全检查，然后再使用 | need support documents of how to manage the USB ports, how to block the USB port access technically. 1. Defined process for governing the use of the removable storage. 2.Defined role to implement, montor and review the use of removable storage. 3. Technology to enforce the removable storage access to workstations. 4. Technology to monitor the use of removable storage and alert for violations. 5. Exception approval and handling / record keeping 6. Process for handling violations. | [6 empty] | 1 | 0
CY-OT207 | Protect | Workstations | Ad-hoc | 2 |  | https://drive.google.com/file/d/1vqkExJJAaG4hCeCeSQ-0vyvXT_SlmOLD/view?usp=share_link | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The deployment of the System hardening configuration following Group system hardening policy. - Deliverables (IT only) - The implementation of the AD security configuration following the Group AD Security Policy (When AD is applicable). - Deliverables - The review and update of security hardening annually. - Deliverables - The record of the exception handling/control with approval. Deliverables - Host based Firewall enabled with default-deny setup. | 2024 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The deployment of the System hardening configuration following Group system hardening policy. - Deliverables (IT only) - The implementation of the AD security configuration following the Group AD Security Policy (When AD is applicable). - Deliverables - The review and update of security hardening annually. - Deliverables - The record of the exception handling/control with approval. Deliverables - Host based Firewall enabled with default-deny setup. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 组系统硬化策略之后的系统硬化配置的部署。 - 可交付成果 - 如果有AD域控，则实施AD域安全策略和检查 - 可交付成果 - 每年对安全性硬化的审查和更新。 - 可交付成果 - 经批准的异常处理/控制的记录。 Exparables-启用了基于主机的防火墙，并使用默认的deny设置。 | * Create information security management documents, cover the required content. * Only allow the service, communication protocol (network port) to be used on the workstation (can be configured on the host firewall, or the communication between the network segments on the network firewall can be limited) * If you have AD domain control, do AD security analysis, and eliminate hidden dangers * Check the safety strategy and configuration at least once a year, and rectify the risks discovered | * 创建信息安全管理文件，涵盖所要求的内容。 * 只允许使用的服务、通讯协议（网络端口）在工作站上运行（可在主机防火墙上配置，或在网络防火墙上对网段之间的通讯做限制） * 如果有AD域控，做AD安全分析，并消除隐患 * 每年至少检查一次安全策略和配置，对发现的风险进行整改 | [7 empty] | 1 | 0
CY-OT210 | Protect | Vulnerability Management | Not applied | 1 | No legacy system. Factory Direct Replacement |  | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The updated list of the legacy and obsolete assets - Deliverables - The proper security protections are applied to the legacy and obsolete assets - Deliverables - The record of the exception handling/control with approval. | 2024 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The updated list of the legacy and obsolete assets - Deliverables - The proper security protections are applied to the legacy and obsolete assets - Deliverables - The record of the exception handling/control with approval. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 旧的和过时资产的更新列表 - 可交付成果 - 适当的安全保护应用于遗产和过时的资产 - 可交付成果 - 经批准的例外处理/控制的记录。 | * Create information security management documents, cover the required content. * Update the old and outdated asset list in time * According to the industrial control information security management policy, the old and outdated assets take appropriate security protection * If there are exceptions, the management process is required to be approved and recorded according to the exception. | * 创建信息安全管理文件，涵盖所要求的内容。 * 及时更新旧的和过时资产清单 * 按照工控信息安全管理政策，对旧的和过时资产采取恰当的安全防护 * 如果有例外情况，需按照例外情况管理流程进行审批，并记录。 | 1. Defined process of Vulnerability management and legacy system lifecycle management 2. Defined roles to handle the legacy system lifecycle management 3. regular Inventory update to the legacy systems and the associated risks. 4. Mitigating risks to acceptable by applying compensating measure to the legacy systems which is operational. 5. exception approval and handling, record keeping. 6. Replacement plan to the legacy systems. | [6 empty] | 1 | 0
CY-OT501 | Recover | Backup Management | Defined | 3 | Data backup is carried out | https://drive.google.com/file/d/1AqZbhesEjoEWlEEdPbBJyTExIwnhQXJ6/view?usp=share_link | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The data backup and recovery plan - Deliverables - The data backup media are encrypted, stored securly and separated from the the source system. - Deliverables - The records of performing the recovery drill and validated regularly. - Deliverables - The data backup retention applied according to the Policy. - Deliverables - High Availablility and/or Disaster Recovery Plan for Critical application / systems meeting the SLA. | 2024 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The data backup and recovery plan - Deliverables - The data backup media are encrypted, stored securly and separated from the the source system. - Deliverables - The records of performing the recovery drill and validated regularly. - Deliverables - The data backup retention applied according to the Policy. - Deliverables - High Availablility and/or Disaster Recovery Plan for Critical application / systems meeting the SLA. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 数据备份和恢复计划 - 可交付成果 - 数据备份介质需要加密，异地存储 - 可交付成果 - 执行恢复训练并定期验证的记录。 - 可交付成果 - 根据政策应用的数据备份保留率。 - 可交付成果 - 对关键应用程序 /系统的高可用性和 /或灾难恢复计划。 | * Create information security management documents, cover the required content. * According to business requirements, formulate data backup and recovery plans, and determine the retaining time of backup data. High reliability and disaster recovery plan meets business requirements. * Data backup medium needs to be encrypted, stored in different places (or stored-fire, waterproof, anti-theft) * At least once a system and data recovery drills each year, and verify its results. | * 创建信息安全管理文件，涵盖所要求的内容。 * 依据业务要求，制定数据备份和恢复计划，并确定备份数据的保留时长。高可靠性和灾难恢复计划要符合业务要求。 * 数据备份介质需要加密，异地存储（或在本地以安全方式存储-防火、防水、防盗） * 每年至少进行一次系统和数据恢复演练，并验证其结果。 | [7 empty] | 1 | 0
CY-OT302 | Detect | Security in Maintenance operations | Defined | 3 | We monitor the access out of our local network | https://drive.google.com/file/d/19pQFzx6QslrufvI-TFkGLVMBgMdK52y_/view?usp=share_link | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The ICS remote access design, which is compliant with the Group's ICS policy for the remote access - Deliverables - The cyber security assessment for ICS remote access - Deliverables - In case of the issues found, the remediation action are carried out. | 2025 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The ICS remote access design, which is compliant with the Group's ICS policy for the remote access - Deliverables - The cyber security assessment for ICS remote access - Deliverables - In case of the issues found, the remediation action are carried out. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 工控远程访问设计，符合该小组的ICS策略用于远程访问 - 可交付成果 - 工控远程访问的网络安全评估 - 可交付成果 - 如果发现的问题，进行了修复行动。 | * Create information security management documents, cover the required content. * If there is a remote access business scenario, remote access to information security specifications, and its schematic diagram * Remote access account management, including but not limited to the account life cycle management process, account creation and authority approval records, account removal records, account lists, etc. * An information security assessment of the existing remote access architecture and its management process every year | * 创建信息安全管理文件，涵盖所要求的内容。 * 如果有远程访问业务场景，远程访问信息安全规范说明，及其示意图 * 远程访问账户管理，包括但不限于账户生命周期管理流程，账户创建和权限审批记录，账户清除记录，账户清单等 * 每年对现有远程访问架构及其管理流程进行信息安全评估 | [7 empty] | 1 | 0
CY-OT203 | Protect | Access Control, Account and Access right management | Ad-hoc | 2 | Validate user accounts | https://docs.google.com/document/d/1ZWe0zeoO6AcEu8vF4qwuQy8hlFDIlJ7m/edit?usp=share_link&ouid=112652071405849358717&rtpof=true&sd=true https://docs.google.com/spreadsheets/d/1CzxfZtInt47KtaLfPsgnNLrLTcHMlL2t/edit#gid=1453586697 https://drive.google.com/file/d/1Rbim8jpYhY8ZeVBL2pXTGLyW2YMuddAe/view?usp=share_link | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The account lifecycle management is integrated with the HR employee management procedures of on joiner, mover and leaver (JML) - Deliverables - The accounts review with the business owners every 6 months. - Deliverables (IT only) - The password policy is deployed in the systems (Servers & workstations) and the applications, which is compliant with the Group password policy. | 2025 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The account lifecycle management is integrated with the HR employee management procedures of on joiner, mover and leaver (JML) - Deliverables - The accounts review with the business owners every 6 months. - Deliverables (IT only) - The password policy is deployed in the systems (Servers & workstations) and the applications, which is compliant with the Group password policy. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 帐户生命周期管理与人力资源雇员管理程序的人力资源员工管理程序集成在一起 - 可交付成果 - 每6个月与企业主进行审查。 - 可交付成果（仅此） - 密码策略被部署在系统（服务器和工作站）和应用程序中，该应用程序符合组密码策略。 | * Create information security management documents, cover the required content. * According to the management requirements, the account is managed to manage the life cycle, and pay attention to cooperating with the employee management process of human resources * Every 6 months shall review the account and its authority by the business supervisor * Password strategy of the password strategy configuration system in accordance with the management requirements | * 创建信息安全管理文件，涵盖所要求的内容。 * 按照管理要求对帐户进行生命周期管理，注意与人力资源的员工管理流程相配合 * 每6个月由业务主管对账户及其权限进行审查 * 按照管理要求中的密码策略配置系统的密码策略 | [7 empty] | 1 | 0
CY-OT204 | Protect | Access Control, Account and Access right management | Defined | 3 | manage use accounts | https://docs.google.com/document/d/1ZWe0zeoO6AcEu8vF4qwuQy8hlFDIlJ7m/edit?usp=share_link&ouid=112652071405849358717&rtpof=true&sd=true https://drive.google.com/file/d/1ozrf7LJyAqvqiy9LiB_ouCYvRjj0-bDH/view?usp=share_link https://docs.google.com/spreadsheets/d/1CzxfZtInt47KtaLfPsgnNLrLTcHMlL2t/edit#gid=1453586697 | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The password policy is deployed in the system and the applications, which is compliant with the Group's password policy. | 2025 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The password policy is deployed in the system and the applications, which is compliant with the Group's password policy. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 密码策略已在系统和应用程序中部署，该应用程序符合集团的密码策略。 | * Create information security management documents, cover the required content. * Password strategy of the password strategy configuration system in accordance with the management requirements | * 创建信息安全管理文件，涵盖所要求的内容。 * 按照管理要求中的密码策略配置系统的密码策略 | 1. Defined process of the user account management (lifecycle management) and password policies to systems and applications 2. Defined role to handle the access control, user management and password policy enforcement 3. Password policy enforcement to systems and applications 4. regular Record for handling user account review / clean up at least 6 months 5. Exception approval and handling / record keeping | [6 empty] | 1 | 0
CY-OT205 | Protect | Workstations | Ad-hoc | 2 | Not Use USB |  | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The deployment of the System hardening configuration following Group system hardening policy. - Deliverables (IT only) - The implementation of the AD security configuration following the Group AD Security Policy (When AD is applicable). - Deliverables - The review and update of security hardening annually. - Deliverables - The record of the exception handling/control with approval. - Deliverables - AV/EDR deployed with Automated updates. | 2025 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The deployment of the System hardening configuration following Group system hardening policy. - Deliverables (IT only) - The implementation of the AD security configuration following the Group AD Security Policy (When AD is applicable). - Deliverables - The review and update of security hardening annually. - Deliverables - The record of the exception handling/control with approval. - Deliverables - AV/EDR deployed with Automated updates. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 组系统硬化策略之后的系统硬化配置的部署。 - 可交付成果 - 如果有AD域控，则实施AD域安全策略和检查 - 可交付成果 - 每年对安全性硬化的审查和更新。 - 可交付成果 - 经批准的异常处理/控制的记录。 - 可交付成果 - 使用自动更新部署的AV/EDR。 | * Create information security management documents, cover the required content. * Working the workstation according to the industrial control information security policy, including but not limited to patch renewal, virus protection, deployment EDR * If you have AD domain control, do AD security analysis, and eliminate hidden dangers * Rectify the risk discovered | * 创建信息安全管理文件，涵盖所要求的内容。 * 按照工控信息安全政策对工作站进行安全加固，包括但不限于补丁更新、病毒防护、部署EDR * 如果有AD域控，做AD安全分析，并消除隐患 * 对发现的风险进行整改 | it is for computer hardening, not only for USB access, like forbid unused network port, antivirus etc. 1. Defined process for Configuration hardening to workstations. 2. Defined role to handle the configuration hardening. 3. Regularly monitor and update the the hardening control to most of the workstations. 4. Review the configraution hardening standard annually. 5. Exception approval and handling / record keeping | [6 empty] | 1 | 0
CY-OT208 | Protect | Network Architecture Principles | Ad-hoc | 2 | OT Area Network | https://drive.google.com/file/d/1vqkExJJAaG4hCeCeSQ-0vyvXT_SlmOLD/view?usp=share_link | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The updated network diagram with the interconnection between IT and OT (when applicable), the data flow and the security control. - Deliverables - The new set up and the update of the network architecture, firewall security policy etc are validated by the BU cyber security team or the cyber security correspondent. - Deliverables - The network segments with ACL are deployed following the Group standard. - Deliverables - OT Network architecure implemented with the Group security guideline. | 2025 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The updated network diagram with the interconnection between IT and OT (when applicable), the data flow and the security control. - Deliverables - The new set up and the update of the network architecture, firewall security policy etc are validated by the BU cyber security team or the cyber security correspondent. - Deliverables - The network segments with ACL are deployed following the Group standard. - Deliverables - OT Network architecure implemented with the Group security guideline. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 具有IT与OT之间互连的更新网络图（如果适用），数据流和安全控制。 - 可交付成果 - 新设置和网络体系结构，防火墙安全策略等的更新由BU网络安全团队或网络安全通讯员验证。 - 可交付成果 - 具有ACL的网络段按照组标准部署。 - 可交付成果 - 使用集团安全指南实现的OT网络架构。 | * Create information security management documents, cover the required content. * Timely update the industrial control network topology (indicating network partition, IP address grouping, data flow, etc.) * Design and implement the industrial control network architecture in accordance with the industrial control information security policy * Do a security filter configuration on the network firewall (or other information security equipment) | * 创建信息安全管理文件，涵盖所要求的内容。 * 及时更新工控网络拓扑图（表明网络分区、IP地址分组、数据流等） * 按照工控信息安全政策设计并实施工控网络架构 * 在网络防火墙（或其它信息安全设备）上做安全过滤配置 | [7 empty] | 1 | 0
CY-OT209 | Protect | Vulnerability Management | Ad-hoc | 2 |  |  | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The tools or records maintaining the patching status of the equipment (should cover servers, workstations, network and security appliance and mobile devices when applicable,) and the applications, including the obsolescent one. - Deliverbables - Record of remediation actions or accepted compensating migtation mesuares to unresolvable vulnerabiities including obsolescent assets and application that are still in use. | 2025 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The tools or records maintaining the patching status of the equipment (should cover servers, workstations, network and security appliance and mobile devices when applicable,) and the applications, including the obsolescent one. - Deliverbables - Record of remediation actions or accepted compensating migtation mesuares to unresolvable vulnerabiities including obsolescent assets and application that are still in use. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 维护设备修补状态的工具或记录（应涵盖服务器，工作站，网络和安全设备以及适用的移动设备）以及包括过时的应用程序。 - 可交付成果 - 修复措施的记录或接受的补偿中的中间人，包括仍在使用的过时资产和应用程序，包括无法解决的漏洞。 | * Create information security management documents, cover the required content. * Implement patch management and operation in accordance with the industrial control information security policy * Rectify the hidden dangers discovered | * 创建信息安全管理文件，涵盖所要求的内容。 * 按照工控信息安全政策实施补丁管理和操作 * 对发现的安全隐患做整改 | 1. Defined Process of Vulnerability Management and patch menagement process 2. Defined Roles to handle vulernability and patch management 3. Monthly vulernability scan and Patching 4. Technology to enforce the scan and patching 5. Exception approval and handling / record keeping | [6 empty] | 1 | 0
CY-OT401 | Respond | Event log management and monitoring | Ad-hoc | 2 | Have the log | https://drive.google.com/file/d/1dLzM420GlI5kzZgYlc5zE-SKUDbHBkoQ/view?usp=share_link | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The centralized logging with the corresponding log types listed in Group policy - Deliverables - The log retention is 6 months at least - Deliverables - The NTP is setup properly to ensure the log records with the accurate time stamp. - Deliverables - The Security monitoring and response. | 2025 | * Create the management document template | N/A | - People - Role(s) defined and responsible for the corresponding security control. - Process - Documented guide(s) or procedure(s) with scope defined. - Deliverables - The centralized logging with the corresponding log types listed in Group policy - Deliverables - The log retention is 6 months at least - Deliverables - The NTP is setup properly to ensure the log records with the accurate time stamp. - Deliverables - The Security monitoring and response. | - 人 - 对相应安全控制的角色定义并负责。 - 过程 - 已定义范围的记录指南或过程。 - 可交付成果 - 集中日志记录，其中包含组策略中列出的相应日志类型 - 可交付成果 - 保留日志至少为6个月 - 可交付成果 - 正确设置NTP，以确保使用准确的时间戳的日志记录。 - 可交付成果 - 安全监控和响应。 | * Create information security management documents, cover the required content. * Join the log management system provided by the headquarters of China. The log retains at least 6 months. Monitoring and response by Chinese headquarters managed safety monitoring and response (local IT operation). * Set time synchronization service (NTP) | * 创建信息安全管理文件，涵盖所要求的内容。 * 加入中国总部提供的日志管理系统。日志至少保留6个月。由由中国总部管理安全监控和响应（本地IT操作）。 * 设置时间同步服务（NTP） | The log includes network device and application systems, not only firewall. And its retention should be 6 months | [6 empty] | 1 | 0